## Milestone3 Scrum Meeting
DAILY SCRUM STAND UP MEETING
GROUP NAME |  | WEEK START dates below will auto populate | SUPERVISOR
Team K |  | 2024-06-08 | Vip Monty
SAT | 2024-06-08
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Vip | Fix: branching | Medium | Corrected branching/test4.txt | Complete
2 | Logan | fix: design doc | Medium |  | In Progress
3 | Tait | Email instructor for more detail reguarding design doc formatting and expected functionality of branching | Medium |  | Complete
4 | Andrew | math function overflow control code | Medium |  | Complete
5 | Team | work on GUI and go over TODO for next time: Audit use cases, add overflow code, make sure branching works. Otherwise, you should be in good shape for milestone 3. | High |  | Complete
6
7
8
9
10
SAT | 2024-06-15
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | TEAM | WORK ON SRS FOR TUESDAYS MEETING(20) | High | due by Tues 6/18/24 | Complete
2 | Logan | GUI Design Doc(10 pts) | Medium | due by Fri 6/21/24 | Complete
3 | Tait | Other Documents(10 pts): Readme.txt | Medium | due by Fri 6/21/24 | In Progress
4 | Andrew | Class Definition Document(15 pts) | Medium | due by Fri 6/21/24 | Complete
5 | Vip | Scrum Master Responsibilities: Merge SRS, Review Submissions and submit | Medium | due by Fri 6/21/24 | In Progress
6
7
8
9
10
... | …
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1
2
3
4
5
6
7
8
9
10
... | …
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1
2
3
4
5
6
7
8
9
10
... | …

## Dropdown Keys - DO NOT DELETE
KEY DROPDOWNS - DO NOT DELETE
| PRIORITY KEY | STATUS KEY
| High | In Progress
| Medium | Ready to Start
| Low | Complete
On Hold
Testing

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.